## contract management c
Contract Management Claims System
Manage any type of project. Assign owners, set timelines and keep track of where your project stands.
To-Do
Name | Status | Due date | Timeline - Start | Timeline - End
Project Planning | Done | 2025-09-09
Project development | Done | 2025-09-09
Submitting | Done | 2025-09-09
Application building | Working on it | 2025-10-14 | 2025-09-12 | 2025-10-14
Editing | Not Started | 2025-10-20 | 2025-10-14 | 2025-10-20
Testing | Not Started | 2025-10-21 | 2025-10-20 | 2025-10-21
Submitting | Not Started | 2025-10-24
Resolving errors | Not Started | 2025-11-08 | 2025-10-31 | 2025-11-08
Editing | Not Started | 2025-11-16 | 2025-11-08 | 2025-11-16
Testing | Not Started | 2025-11-16 | 2025-11-15 | 2025-11-16
Submitting | Not Started | 2025-11-21
|  | 2025-09-09 to 2025-11-21 | 2025-09-12 | 2025-11-16